## Worksheet
Thailand : : TEAM B : : Audit support
Steps |  |  |  |  | 1.Send FS and detail to auditor. |  |  | 2.Make and send bank and AP/AR confirmation |  |  | 3.Clear point from auditor. |  |  | 4.Get draft FS from auditor |  |  | 5.Check draft FS |  |  | 6.Send to client |  |  | 7.Get sign from client on Draft FS. |  |  | 8.Get the original from auditor
Client Name | Team | PIC 1 | PIC 2 | Month | Last | Target | Completed | Last | Target | Completed | Last | Target | Completed | Last | Target | Completed | Last | Target | Completed | Last | Target | Completed | Last | Target | Completed | Last | Target | Completed
1.AIDS Healthcare Foundation | TEAM B | Aim | - | December |  | 10/02/2023 | 13/02/2023 |  | 15/02/2023 | 15/02/2023 |  | 31/03/2023 | 03/04/2023 |  | 01/04/2023 | 03/04/2023 |  | 01/04/2023 | 03/04/2023 |  | 01/04/2023 | 03/04/2023 |  | 06/04/2023 |  |  | 05/04/2023
2.Asahi Intecc Co.,Ltd | TEAM B | Jenny | Aim | March |  | 14/04/2023 |  |  | 14/04/2023 |  |  | 31/05/2023 |  |  | 31/05/2023 |  |  | 31/05/2023 |  |  | 31/05/2023 |  |  | 31/05/2023 |  |  | 31/05/2023
3.BB and BEDEV CO.,LTD. | TEAM B | Piano | Porpia | May |  | 30/06/2023 |  |  | 30/06/2023 |  |  | 31/07/2023 |  |  | 31/08/2023 |  |  | 30/09/2023 |  |  | 25/10/2023 |  |  | 31/10/2023 |  |  | 31/10/2023
4.CHUO SSK | TEAM B | Frank | Porpia | August |  | 31/10/2023 |  |  | 31/10/2023 |  |  | 31/10/2023 |  |  | 31/10/2023 |  |  | 30/11/2023 |  |  | 30/11/2023 |  |  | 30/11/2023 |  |  | 30/11/2023
5.CYC Metal (Thailand) Co.,Ltd | TEAM B | Kao | Aim | July |  | 31/08/2023 |  |  | 31/08/2023 |  |  | 31/08/2023 |  |  | 30/09/2023 |  |  | 30/09/2023 |  |  | 30/09/2023 |  |  | 30/09/2023 |  |  | 30/09/2023
6.CYC Metal (Thailand) Co.,Ltd. | TEAM B | Kao | May | November |  | 01/11/2023 |  |  | 03/11/2023 |  |  | 10/11/2023 |  |  | 15/11/2023 |  |  | 17/11/2023 |  |  | 22/11/2023 |  |  | 24/11/2023 |  |  | 29/11/2023
7.DAISEI EVERY 24(THAILAND) CO., LTD. | TEAM B | Jenny | Mui | December |  | 01/02/2023 | 08/02/2023 |  | 03/02/2023 | 08/02/2023 |  | 27/02/2023 | 28/02/2023 |  | 17/03/2023 | 17/03/2023 |  | 24/03/2023 | 27/03/2023 |  | 24/03/2023 | 27/03/2023 |  | 05/04/2023 | 05/04/2023 |  | 05/04/2023 | 05/04/2023
8.DAIWA Harness (Thailand) Co.,Ltd. | TEAM B | Tong | Mui | March |  | 30/06/2023 |  |  | 30/06/2023 |  |  | 30/06/2023 |  |  | 31/07/2023 |  |  | 31/07/2023 |  |  | 31/07/2023 |  |  | 31/07/2023 |  |  | 31/07/2023
9.JASCO (Thailand) Co.,Ltd. | TEAM B | Piano | Porpia | February |  | 31/03/2023 | 04/04/2023 |  | 10/04/2023 | 04/04/2023 |  | 17/04/2023 |  |  | 21/04/2023 |  |  | 21/04/2023 |  |  | 21/04/2023 |  |  | 28/04/2023 |  |  | 28/04/2023
10.MEGA TECH (THAI) CO.,LTD. | TEAM B | Mui | Mui | June |  | 31/08/2023 |  |  | 31/07/2023 |  |  | 25/09/2023 |  |  | 29/09/2023 |  |  | 02/10/2023 |  |  | 23/10/2023 |  |  | 27/10/2023 |  |  | 30/10/2023
11.Miyama Precision (Thailand) Co.,Ltd. | TEAM B | Kao | May | February |  | 01/06/2023 |  |  | 07/06/2023 |  |  | 14/06/2023 |  |  | 20/06/2023 |  |  | 19/05/2023 |  |  | 23/05/2023 |  |  | 29/05/2023 |  |  | 09/06/2023
12.NANKAI EXPRESS (THAILAND) CO.,LTD. | TEAM B | Frank, Jenny | Aim | January | 08/02/2023 | 07/02/2024 |  | 14/02/2023 | 14/02/2024 |  | 01/03/2023 | 24/02/2024 |  | 01/03/2023 | 22/02/2024 |  | 01/03/2023 | 28/02/2024 |  | 01/03/2023 | 28/02/2024 |  | 27/03/2023 | 24/03/2024 |  | 03/04/2023 | 31/03/2024
13.RKH ENGINEERINGandSERVICE (THAILAND) CO.,LTD | TEAM B | Tong | Porpia | December |  | 31/03/2023 | 05/04/2023 |  | 31/03/2023 | 05/04/2023 |  | 31/03/2023 | 05/04/2023 |  | 18/04/2023 | 05/04/2023 |  | 19/04/2023 |  |  | 20/04/2023 |  |  | 30/04/2023 |  |  | 05/05/2023
14.Stradustries | TEAM B | Frank | Porpia | December |  | 31/03/2023 |  |  | 31/03/2023 |  |  | 07/04/2023 |  |  | 25/04/2023 |  |  | 26/04/2023 |  |  | 30/04/2023 |  |  | 03/05/2023 |  |  | 05/05/2023
15.THAI MICRO CO.,LTD. | TEAM B | Piano | Aim | January |  | 22/03/2023 | 22/03/2023 |  | 24/03/2023 | 24/03/2023 |  | 05/04/2023 |  |  | 04/04/2023 |  |  | 04/04/2023 |  |  | 04/04/2023 |  |  | 14/04/2023 |  |  | 30/04/2023
16.Treasure Factory (Thailand) Co,.Ltd. | TEAM B | Tong | May | November |  | 27/01/2023 | 30/01/2023 |  | 03/02/2023 | 08/02/2023 |  | 24/02/2023 | 28/02/2023 |  | 27/02/2023 | 28/02/2023 |  | 28/02/2023 | 28/02/2023 |  | 17/03/2023 | 22/03/2023 |  | 31/03/2023 | 05/04/2023 |  | 31/03/2023 | 05/04/2023
17.Yoshu Thailand | TEAM B | Frank | Mui | January |  | 06/04/2023 |  |  | 21/04/2023 |  |  | 25/05/2023 |  |  | 01/06/2023 |  |  | 05/06/2023 |  |  | 05/06/2023 |  |  | 09/06/2023 |  |  | 15/06/2023