## Worksheet
Thailand : : Audit support
Steps |  |  |  |  | 1.Send FS and detail to auditor. |  | 2.Make and send bank and AP/AR confirmation |  | 3.Clear point from auditor. |  | 4.Get draft FS from auditor |  | 5.Check draft FS |  | 6.Send to client |  | 7.Get sign from client on Draft FS. |  | 8.Get the original from auditor
Client Name | Team | PIC 1 | PIC 2 | Month | Target | Completed | Target | Completed | Target | Completed | Target | Completed | Target | Completed | Target | Completed | Target | Completed | Target | Completed
1. KEM (THAILAND) CO., LTD. | TEAM A | - | - | June | Not set |  | Not set |  | Not set |  | Not set |  | Not set |  | Not set |  | Not set |  | Not set
2.AIDS Healthcare Foundation | TEAM B | Aim | - | December | 10/02/2023 | 13/02/2023 | 15/02/2023 | 15/02/2023 | 31/03/2023 | 03/04/2023 | 01/04/2023 | 03/04/2023 | 01/04/2023 | 03/04/2023 | 01/04/2023 | 03/04/2023 | 06/04/2023 |  | 05/04/2023
3.AMADA ORII | TEAM A | Care | Vy | March | 06/06/2023 |  | 12/06/2023 |  | 19/06/2023 |  | 17/07/2023 |  | 17/07/2023 |  | 18/07/2023 |  | 20/07/2023 |  | 21/07/2023
4.AMADA Press | TEAM A | Care | Vy | March | 06/06/2023 |  | 12/06/2023 |  | 19/06/2023 |  | 17/07/2023 |  | 17/07/2023 |  | 18/07/2023 |  | 20/07/2023 |  | 21/07/2023
5.Asahi Intecc Co.,Ltd | TEAM B | Jenny | Aim | March | 14/04/2023 |  | 14/04/2023 |  | 31/05/2023 |  | 31/05/2023 |  | 31/05/2023 |  | 31/05/2023 |  | 31/05/2023 |  | 31/05/2023
6.ASAHI SEIKEI | TEAM C | Neam | Kik | December | 05/04/2023 |  | 07/04/2023 |  | 24/04/2023 |  | 26/04/2023 |  | 27/04/2023 |  | 30/04/2023 |  | 03/05/2023 |  | 05/05/2023
7.ATAGO（Thailand） | TEAM A | Fern | Vy | December | 06/03/2023 | 08/03/2023 | 07/03/2023 | 08/03/2023 | 31/03/2023 | 28/03/2023 | 20/04/2023 |  | 20/04/2023 |  | 20/04/2023 |  | 24/04/2023 |  | 24/04/2023
8.BB and BEDEV CO.,LTD. | TEAM B | Piano | Porpia | May | 30/06/2023 |  | 30/06/2023 |  | 31/07/2023 |  | 31/08/2023 |  | 30/09/2023 |  | 25/10/2023 |  | 31/10/2023 |  | 31/10/2023
9.Big Country | TEAM A | Jean | Wi | December | 17/04/2023 |  | 18/04/2023 |  | 19/04/2023 |  | 27/04/2023 |  | 28/04/2023 |  | 28/04/2023 |  | 28/04/2023 |  | 28/04/2023
10.BLUE PI CO.,LTD. | TEAM D | Pao | Lin | December | 01/02/2023 | 01/02/2023 | 09/03/2023 | 08/03/2023 | 07/04/2023 |  | 10/04/2023 |  | 11/04/2023 |  | 20/04/2023 |  | 25/04/2023 |  | 01/05/2023
11.Bright and Better Co., Ltd. | TEAM E | New | Ake | December | 25/01/2023 | 30/01/2023 | 31/01/2023 | 30/01/2023 | 31/01/2023 | 30/01/2023 | 28/02/2023 | 01/03/2023 | 28/02/2023 | 01/03/2023 | 01/03/2023 | 01/03/2023 | 10/03/2023 | 14/03/2023 | 17/03/2023 | 21/03/2023
12.Carton Optical (Siam) Co., Ltd. | TEAM A | Mai | Wi | March | 17/04/2023 |  | 24/04/2023 |  | 01/05/2023 |  | 15/05/2023 |  | 16/05/2023 |  | 18/05/2023 |  | 19/05/2023 |  | 26/05/2023
13.Carton Trading Co.,Ltd. | TEAM A | Mai | Wi | December | 24/03/2023 | 15/03/2023 | 24/03/2023 | 15/03/2023 | 24/03/2023 | 15/03/2023 | 14/04/2023 | 15/03/2023 | 14/04/2023 | 15/03/2023 | 15/04/2023 | 15/03/2023 | 17/04/2023 | 15/03/2023 | 20/04/2023 | 29/03/2023
14.Champion Foods Co.,Ltd | TEAM A | Jean, Auu, Care | Jame | December | 03/02/2023 | 08/02/2023 | 06/02/2023 | 08/02/2023 | 13/02/2023 | 15/02/2023 | 22/02/2023 | 22/02/2023 | 23/02/2023 | 28/02/2023 | 24/02/2023 | 28/02/2023 | 27/02/2023 | 28/02/2023 | 28/02/2023 | 01/03/2023
15.CHUO SSK | TEAM B | Frank | Porpia | August | 31/10/2023 |  | 31/10/2023 |  | 31/10/2023 |  | 31/10/2023 |  | 30/11/2023 |  | 30/11/2023 |  | 30/11/2023 |  | 30/11/2023
16.CRE | TEAM C | Aim2 | Aor | May | 20/06/2023 |  | 23/06/2023 |  | 04/09/2023 |  | 07/09/2023 |  | 08/09/2023 |  | 13/09/2023 |  | 19/09/2023 |  | 20/09/2023
17.CYC Metal (Thailand) Co.,Ltd | TEAM B | Kao | Aim | July | 31/08/2023 |  | 31/08/2023 |  | 31/08/2023 |  | 30/09/2023 |  | 30/09/2023 |  | 30/09/2023 |  | 30/09/2023 |  | 30/09/2023
18.CYC Metal (Thailand) Co.,Ltd. | TEAM B | Kao | May | November | 01/11/2023 |  | 03/11/2023 |  | 10/11/2023 |  | 15/11/2023 |  | 17/11/2023 |  | 22/11/2023 |  | 24/11/2023 |  | 29/11/2023
19.DAISEI EVERY 24(THAILAND) CO., LTD. | TEAM B | Jenny | Mui | December | 01/02/2023 | 08/02/2023 | 03/02/2023 | 08/02/2023 | 27/02/2023 | 28/02/2023 | 17/03/2023 | 17/03/2023 | 24/03/2023 | 27/03/2023 | 24/03/2023 | 27/03/2023 | 05/04/2023 | 05/04/2023 | 05/04/2023 | 05/04/2023
20.DAIWA Asia Limited | TEAM D | Jim | Lin | March | 05/05/2023 |  | 05/05/2023 |  | 21/06/2023 |  | 30/06/2023 |  | 05/07/2023 |  | 20/07/2023 |  | 31/07/2023 |  | 04/08/2023
21.DAIWA Harness (Thailand) Co.,Ltd. | TEAM B | Tong | Mui | March | 30/06/2023 |  | 30/06/2023 |  | 30/06/2023 |  | 31/07/2023 |  | 31/07/2023 |  | 31/07/2023 |  | 31/07/2023 |  | 31/07/2023
22.ESCON JAPAN (THAILAND) Co.,Ltd. | TEAM D | Ammy | - | December | 19/12/2023 |  | 19/12/2023 |  | 02/03/2024 |  | 03/02/2024 |  | 03/02/2024 |  | 06/02/2024 |  | 15/02/2024 |  | 31/03/2024
23.EYE lighting Co,.Ltd. | TEAM E | Ake | - | December | 24/02/2023 | 27/02/2023 | 24/02/2023 | 27/02/2023 | 15/03/2023 | 15/03/2023 | 31/03/2023 | 31/03/2023 | 31/03/2023 | 31/03/2023 | 01/04/2023 | 31/03/2023 | 07/04/2023 | 31/03/2023 | 17/04/2023
24.FKK (Thailand) Co.,Ltd. | TEAM C | pakgad | Miw | September | 08/11/2023 |  | 08/11/2023 |  | 16/12/2023 |  | 20/12/2023 |  | 20/12/2023 |  | 23/12/2023 |  | 23/12/2023 |  | 07/02/2024
25.FKNE Co.,Ltd. | TEAM D | Bam | Ammy | September | 01/11/2023 |  | 07/11/2023 |  | 04/01/2024 |  | 10/01/2024 |  | 10/01/2024 |  | 10/01/2024 |  | 25/01/2024 |  | 31/01/2024
26.FUJIFILM Digital Solutions (Thailand) Co., Ltd. | TEAM D | Ammy | Eiw | March | 12/04/2023 |  | 17/04/2023 |  | 24/04/2023 |  | 05/05/2023 |  | 12/05/2023 |  | 16/05/2023 |  | 18/05/2023 |  | 19/05/2023
27.Havix | TEAM E | Ake | - | December | 28/02/2023 | 01/03/2023 | 28/02/2023 | 01/03/2023 | 13/03/2023 | 14/03/2023 | 31/03/2023 | 22/03/2023 | 03/04/2023 | 22/03/2023 | 03/04/2023 | 22/03/2023 | 17/04/2023 | 22/03/2023 | 20/04/2023 | 22/03/2023
28.HONDA DENSHI | TEAM A | Auu | Vy | September | 01/12/2023 |  | 04/12/2023 |  | 11/12/2023 |  | 18/12/2023 |  | 19/12/2023 |  | 19/12/2023 |  | 25/12/2023 |  | 25/12/2023
29.Izawa Metal (Thailand) Co.,Ltd. | TEAM A | Mai, Fern | Wi | December | 06/03/2023 | 08/03/2023 | 10/03/2023 | 08/03/2023 | 30/03/2023 | 05/04/2023 | 12/04/2023 |  | 12/04/2023 |  | 13/04/2023 |  | 14/04/2023 |  | 15/04/2023
30.IZAWA METAL TRADING THAILAND CO.,LTD | TEAM A | Mai | Wi | December | 03/03/2023 | 15/03/2023 | 06/03/2023 | 15/03/2023 | 13/04/2023 |  | 18/04/2023 |  | 19/04/2023 |  | 20/04/2023 |  | 25/04/2023 |  | 25/04/2023
31.JASCO (Thailand) Co.,Ltd. | TEAM B | Piano | Porpia | February | 31/03/2023 | 04/04/2023 | 10/04/2023 | 04/04/2023 | 17/04/2023 |  | 21/04/2023 |  | 21/04/2023 |  | 21/04/2023 |  | 28/04/2023 |  | 28/04/2023
32.Kasumigaseki capital (Thailand) Co.,Ltd. | TEAM D | Pao | Eiw | December | 10/01/2024 |  | 10/01/2024 |  | 27/01/2024 |  | 30/01/2024 |  | 31/01/2024 |  | 01/02/2024 |  | 07/02/2024 |  | 15/02/2024
33.KEM (Thailand) Co.,Ltd. | TEAM A | Mai | Jame | December | 20/03/2023 | 14/03/2023 | 21/03/2023 | 21/03/2023 | 10/04/2023 |  | 17/04/2023 |  | 17/04/2023 |  | 18/04/2023 |  | 19/04/2023 |  | 20/04/2023
34.Kuraray SP | TEAM A | Vy | Vy | December | 01/03/2023 | 01/03/2023 | 06/03/2023 | 08/03/2023 | 13/03/2023 | 14/03/2023 | 17/03/2023 | 21/03/2023 | 20/03/2023 | 21/03/2023 | 20/03/2023 | 21/03/2023 | 27/03/2023 | 28/03/2023 | 27/03/2023 | 28/03/2023
35.Kuraray Thailand | TEAM A | Vy | Vy | December | 01/03/2023 | 01/03/2023 | 06/03/2023 | 08/03/2023 | 13/03/2023 | 14/03/2023 | 17/03/2023 | 21/03/2023 | 20/03/2023 | 21/03/2023 | 20/03/2023 | 21/03/2023 | 27/03/2023 | 28/03/2023 | 27/03/2023 | 28/03/2023
36.Marvel Media (Thailand) Co.,Ltd | TEAM Management | Ploy | Ploy | March | 10/06/2023 |  | 12/06/2023 |  | 20/06/2023 |  | 26/06/2023 |  | 27/06/2023 |  | 30/06/2023 |  | 05/07/2023 |  | 10/07/2023
37.Marvel Media Holding Co., Ltd | TEAM Management | Ploy | Ploy | March | 10/06/2023 |  | 12/06/2023 |  | 20/06/2023 |  | 26/06/2023 |  | 27/06/2023 |  | 30/06/2023 |  | 05/07/2023 |  | 10/07/2023
38.MEGA TECH (THAI) CO.,LTD. | TEAM B | Mui | Mui | June | 31/08/2023 |  | 31/07/2023 |  | 25/09/2023 |  | 29/09/2023 |  | 02/10/2023 |  | 23/10/2023 |  | 27/10/2023 |  | 30/10/2023
39.MEIKO ELECTRONICS (THAILAND) CO.,LTD | TEAM C | pakgad | - | December | 24/01/2023 | 24/01/2023 | 27/01/2023 | 24/01/2023 | 08/03/2023 | 10/03/2023 | 09/03/2023 | 10/03/2023 | 13/03/2023 | 10/03/2023 | 15/03/2023 | 10/03/2023 | 28/03/2023 | 05/04/2023 | 31/03/2023 | 05/04/2023
40.Mercuria (Thailand) Co.,Ltd. | TEAM D | Bam | Toei | December | 12/01/2024 |  | 13/01/2024 |  | 23/01/2024 |  | 24/01/2024 |  | 24/01/2024 |  | 03/02/2024 |  | 22/02/2024 |  | 28/02/2024
41.Mercuria SPV | TEAM D | Bam | Toei | December | 10/01/2024 |  | 12/01/2024 |  | 27/01/2024 |  | 31/01/2024 |  | 31/01/2024 |  | 03/02/2024 |  | 22/02/2024 |  | 28/02/2024
42.Mercuria SPV2 | TEAM D | Bam | Toei | December | 10/01/2024 |  | 12/01/2024 |  | 27/01/2024 |  | 31/01/2024 |  | 31/01/2024 |  | 03/02/2024 |  | 22/02/2024 |  | 28/02/2024
43.Mercuria SPV3 | TEAM D | Bam | Toei | December | 10/01/2024 |  | 12/01/2024 |  | 27/01/2024 |  | 31/01/2024 |  | 31/01/2024 |  | 03/02/2024 |  | 22/02/2024 |  | 28/02/2024
44.MICRON (THAILAND) CO.,LTD. | TEAM A | Fern | Vy | March | 12/06/2023 |  | 19/06/2023 |  | 28/06/2023 |  | 07/07/2023 |  | 07/07/2023 |  | 07/07/2023 |  | 10/07/2023 |  | 13/07/2023
45.Miyago | TEAM C | Kik | Kik | May | 18/08/2023 |  | 22/08/2023 |  | 06/10/2023 |  | 10/10/2023 |  | 10/10/2023 |  | 12/10/2023 |  | 20/10/2023 |  | 25/10/2023
46.Miyama Precision (Thailand) Co.,Ltd. | TEAM B | Kao | May | February | 01/06/2023 |  | 07/06/2023 |  | 14/06/2023 |  | 20/06/2023 |  | 19/05/2023 |  | 23/05/2023 |  | 29/05/2023 |  | 09/06/2023
47.MS MOLD (Thailand) CO.,LTD | TEAM D | Pao | Eiw | December | 02/02/2023 | 02/02/2023 | 03/02/2023 | 13/02/2023 | 06/03/2023 | 07/03/2023 | 12/04/2023 |  | 19/04/2023 |  | 20/04/2023 |  | 24/04/2023 |  | 26/04/2023
48.MST Coporation Thai Co.,Ltd. | TEAM D | Bam | Toei | December | 01/02/2023 | 01/02/2023 | 03/03/2023 | 03/03/2023 | 07/04/2023 |  | 10/04/2023 |  | 17/04/2023 |  | 19/04/2023 |  | 28/04/2023 |  | 09/05/2023
49.Nakamura Electric (VC) | TEAM A | Mai, Fern | Wi | December | 20/02/2023 | 21/02/2023 | 06/03/2023 | 08/03/2023 | 17/03/2023 | 21/03/2023 | 24/03/2023 | 21/03/2023 | 24/03/2023 |  | 24/03/2023 |  | 24/03/2023 |  | 25/03/2023
50.NANKAI EXPRESS (THAILAND) CO.,LTD. | TEAM B | Frank, Jenny | Aim | January | 07/02/2024 |  | 14/02/2024 |  | 24/02/2024 |  | 22/02/2024 |  | 28/02/2024 |  | 28/02/2024 |  | 24/03/2024 |  | 31/03/2024
51.Nippon Kayaku (Thailand) Co., Ltd. | TEAM C | Neam | Rung | March | 10/04/2023 |  | 11/04/2023 |  | 24/04/2023 |  | 26/04/2023 |  | 27/04/2023 |  | 28/04/2023 |  | 02/05/2023 |  | 05/05/2023
52.NT Tool Thai Co., Ltd. | TEAM C | Neam | Rung | March | 30/04/2023 |  | 30/04/2023 |  | 31/05/2023 |  | 10/06/2023 |  | 19/06/2023 |  | 23/06/2023 |  | 30/06/2023 |  | 06/07/2023
53.OG Trading ( Thailand ) | TEAM C | Kik | Kik | December | 26/01/2024 |  | 27/01/2024 |  | 10/02/2024 |  | 13/02/2024 |  | 17/02/2024 |  | 17/02/2024 |  | 28/02/2024 |  | 07/03/2024
54.Omori (Thailand) Co., Ltd. | TEAM C | Kik | Kik | May | 09/06/2023 |  | 09/06/2023 |  | 02/08/2023 |  | 04/08/2023 |  | 07/08/2023 |  | 08/08/2023 |  | 08/08/2023 |  | 08/08/2023
55.Oriental Motor (Thailand) Co., Ltd. | TEAM D | Eiw | Eiw | March | 20/04/2023 |  | 10/04/2023 |  | 22/05/2023 |  | 23/05/2023 |  | 25/05/2023 |  | 25/05/2023 |  | 05/06/2023 |  | 15/06/2023
56.PUMI Travel Co., Ltd. | TEAM D | Jim | Eiw | December | 06/02/2023 | 06/02/2023 | 10/02/2023 | 10/02/2023 | 27/02/2023 | 27/02/2023 | 10/04/2023 |  | 11/04/2023 |  | 11/04/2023 |  | 12/04/2023 |  | 12/04/2023
57.RINGER HUT(THAILAND)CO.,LTD. | TEAM A | Jean, Care, Auu | Jame | December | 03/02/2023 | 08/02/2023 | 06/02/2023 | 08/02/2023 | 13/02/2023 | 15/02/2023 | 22/02/2023 | 22/02/2023 | 23/02/2023 | 28/02/2023 | 24/02/2023 | 28/02/2023 | 27/02/2023 | 28/02/2023 | 28/02/2023 | 01/03/2023
58.RKH ENGINEERINGandSERVICE (THAILAND) CO.,LTD | TEAM B | Tong | Porpia | December | 31/03/2023 | 05/04/2023 | 31/03/2023 | 05/04/2023 | 31/03/2023 | 05/04/2023 | 18/04/2023 | 05/04/2023 | 19/04/2023 |  | 20/04/2023 |  | 30/04/2023 |  | 05/05/2023
59.Saishunkan Pharmaceutical (Thailand) Co.,Ltd. | TEAM C | Aim2 | Kik | March | 04/05/2023 |  | 04/05/2023 |  | 22/06/2023 |  | 26/06/2023 |  | 27/06/2023 |  | 28/06/2023 |  | 03/07/2023 |  | 06/07/2023
60.SB SHOWA | TEAM E | Ake | - | December | 28/02/2023 | 01/03/2023 | 28/02/2023 | 01/03/2023 | 17/03/2023 | 21/03/2023 | 18/03/2023 | 22/03/2023 | 18/03/2023 | 22/03/2023 | 20/03/2023 | 22/03/2023 | 21/03/2023 | 22/03/2023 | 22/03/2023 | 22/03/2023
61.Seidensha | TEAM A | Aae | Mint | December | 27/02/2023 | 28/02/2023 | 06/03/2023 | 08/03/2023 | 29/03/2023 | 29/03/2023 | 17/04/2023 |  | 19/04/2023 |  | 20/04/2023 |  | 26/04/2023 |  | 28/04/2023
62.Siam Sun Engineering Co., Ltd. | TEAM C | Sun | Rung | October | 06/02/2024 |  | 06/02/2024 |  | 17/02/2024 |  | 19/02/2024 |  | 22/02/2024 |  | 22/02/2024 |  | 28/02/2024 |  | 07/03/2024
63.SMT ASSET MANAGEMENT Co.,Ltd. | TEAM D | Bam | Toei | December | 10/01/2024 |  | 11/01/2024 |  | 20/01/2024 |  | 24/01/2024 |  | 24/01/2024 |  | 27/01/2024 |  | 22/02/2024 |  | 28/02/2024
64.SOTETSU | TEAM C | Sun | - | December | 08/02/2023 | 09/02/2023 | 13/02/2023 | 15/02/2023 | 02/03/2023 | 07/03/2023 | 03/03/2023 | 07/03/2023 | 06/03/2023 | 07/03/2023 | 09/03/2023 | 10/03/2023 | 24/03/2023 | 21/03/2023 | 28/03/2023 | 28/03/2023
65.Stradustries | TEAM B | Frank | Porpia | December | 31/03/2023 |  | 31/03/2023 |  | 07/04/2023 |  | 25/04/2023 |  | 26/04/2023 |  | 30/04/2023 |  | 03/05/2023 |  | 05/05/2023
66.SUNTORY BEVERAGE and FOOD ASIA PTE. LTD. | TEAM A | Mai | Mint | December | 16/01/2023 | 08/02/2023 | 23/01/2023 | 08/02/2023 | 20/03/2023 | 20/03/2023 | 06/04/2023 | 05/04/2023 | 06/04/2023 | 05/04/2023 | 06/04/2023 |  | 07/04/2023 |  | 09/04/2023
67.Taisei Techno (Thailand) Co., Ltd. | TEAM D | Jim | - | December | 22/03/2023 | 22/03/2023 | 06/04/2023 |  | 07/04/2023 |  | 12/04/2023 |  | 14/04/2023 |  | 15/04/2023 |  | 20/04/2023 |  | 25/04/2023
68.TCF Legal Firm Co., Ltd. | TEAM E | New | Ake | December | 28/02/2023 | 01/03/2023 | 28/02/2023 | 01/03/2023 | 01/03/2023 | 01/03/2023 | 14/04/2023 |  | 14/04/2023 |  | 14/04/2023 |  | 17/04/2023 |  | 20/03/2023
69.TCF Management Recruitment Co., Ltd. | TEAM E | New | Ake | December | 28/02/2023 | 01/03/2023 | 28/02/2023 | 01/03/2023 | 01/03/2023 | 01/03/2023 | 07/04/2023 |  | 07/04/2023 |  | 10/04/2023 |  | 10/04/2023 |  | 14/04/2023
70.THAI MICRO CO.,LTD. | TEAM B | Piano | Aim | January | 22/03/2023 | 22/03/2023 | 24/03/2023 | 24/03/2023 | 05/04/2023 |  | 04/04/2023 |  | 04/04/2023 |  | 04/04/2023 |  | 14/04/2023 |  | 30/04/2023
71.THAI SOKEN CO.,LTD. | TEAM Management | Ploy | Ploy | September | 20/11/2023 |  | 21/11/2023 |  | 24/11/2023 |  | 15/12/2023 |  | 18/12/2023 |  | 20/12/2023 |  | 25/12/2023 |  | 27/12/2023
72.Toho Industry (Thailand) Co., Ltd. | TEAM C | Noey | Kik | March | 12/04/2023 |  | 12/04/2023 |  | 24/05/2023 |  | 29/05/2023 |  | 30/05/2023 |  | 31/05/2023 |  | 02/06/2023 |  | 07/06/2023
73.Tokyo Consulting Firm Co.,Ltd. | TEAM E | New | Ake | December | 28/02/2023 | 01/03/2023 | 28/02/2023 | 01/03/2023 | 08/03/2023 | 01/03/2023 | 14/04/2023 |  | 14/04/2023 |  | 17/04/2023 |  | 17/04/2023 |  | 20/04/2023
74.Tokyo Sumida Co.,Ltd | TEAM D | Jim | Eiw | December | 06/01/2024 |  | 09/01/2024 |  | 24/01/2024 |  | 10/03/2024 |  | 13/03/2024 |  | 14/03/2024 |  | 22/03/2024 |  | 29/03/2024
75.Treasure Factory (Thailand) Co,.Ltd. | TEAM B | Tong | May | November | 27/01/2023 | 30/01/2023 | 03/02/2023 | 08/02/2023 | 24/02/2023 | 28/02/2023 | 27/02/2023 | 28/02/2023 | 28/02/2023 | 28/02/2023 | 17/03/2023 | 22/03/2023 | 31/03/2023 | 05/04/2023 | 31/03/2023 | 05/04/2023
76.Tsuchiyoshi(HRVC) | TEAM A | Aae | Mint | March | 06/06/2023 |  | 30/04/2023 |  | 16/06/2023 |  | 23/06/2023 |  | 26/06/2023 |  | 29/06/2023 |  | 30/06/2023 |  | 30/06/2023
77.Uchinuki (Thailand) Co.,Ltd. | TEAM C | Sun | Kik | January | 23/01/2024 |  | 23/01/2024 |  | 09/03/2024 |  | 10/03/2024 |  | 13/03/2024 |  | 15/03/2024 |  | 24/03/2024 |  | 03/04/2024
78.Uchinuki Industry (Thailand) Co.,Ltd. | TEAM C | Sun | Kik | May | 19/06/2023 |  | 19/06/2023 |  | 05/09/2023 |  | 07/09/2023 |  | 08/09/2023 |  | 11/09/2023 |  | 13/09/2023 |  | 15/09/2023
79.Yokota Mortor (Thailand) Co., Ltd. | TEAM D | Pao | Eiw | December | 18/01/2024 |  | 18/01/2024 |  | 27/01/2024 |  | 30/01/2024 |  | 31/01/2024 |  | 01/02/2024 |  | 02/02/2024 |  | 03/02/2024
80.Yoshu CS metal works Co.,Ltd. | TEAM D | Ammy | Toei | September | 10/11/2023 |  | 04/11/2023 |  | 15/12/2023 |  | 16/12/2023 |  | 22/12/2023 |  | 23/12/2023 |  | 06/01/2024 |  | 10/01/2024
81.Yoshu Thailand | TEAM B | Frank | Mui | January | 06/04/2023 |  | 21/04/2023 |  | 25/05/2023 |  | 01/06/2023 |  | 05/06/2023 |  | 05/06/2023 |  | 09/06/2023 |  | 15/06/2023
82.YTF (Thailand) Co., Ltd. | TEAM D | Ammy | Toei | December | 31/01/2024 |  | 10/02/2024 |  | 23/02/2024 |  | 23/02/2024 |  | 01/03/2024 |  | 01/03/2024 |  | 15/03/2024 |  | 24/03/2024
83.Zen Foods (Thai) Co.,Ltd. | TEAM C | Aim2 | Noey | December | 24/02/2023 | 27/02/2023 | 10/03/2023 | 10/03/2023 | 11/04/2023 |  | 18/04/2023 |  | 19/04/2023 |  | 20/04/2023 |  | 21/04/2023 |  | 25/04/2023